## UAT_Instruction sheet
Test instructions
Service: | Publish on Portal
UAT period: | 30 June to 11 July 2025
How to use this document | 1. Each tab in this document is a different test scenario. 2. When you view each test scenario e.g.A-PAN-UAT_001, there are a series of steps for you to complete. Where no information is provided, please enter a value of your choice / information to progress the application. 3. Please ensure that you enter the outcome of each step in the spreadsheet as you complete the testing. 4. If the step does not return the expected result, please include a screenshot of the issue and a description of what has occurred next to the test step within this document. 5. Once you have completed the scenario, enter the outcome of the testing in the 'Test outcome' table below.
What is considered to be a 'Fail'? | The focus of user acceptance testing is to validate that a user can complete a particular workflow. A Fail should only be noted as the outcome, if the expected results are not experienced.
What to do once you have completed the test scenarios in this document | Once you have completed the test scenarios within this document, please: 1. Update the 'Test outcome' table below with the test results. 2. Rename this file using the naming convention: [your name] - [service] - Test instructions_[ddmmyyyy]. For example: John Citizen – Publish on portal – Test instructions_30062025. 3. Return this file to the team via email to uatplanning@dphi.nsw.gov.au. Please use the subject line: UAT test outcome. The team will review the outcome of your testing and may contact you if they have any further questions.
I need help! What do I do? | If you need assistance completing the test scenario, please reach out to the team on email: uatplanning@dphi.nsw.gov.au
Test outcome
Scenario | Pass | Fail
A-PAN-UAT_001 |  | FAIL
A-PAN-UAT_002 |  | FAIL
A-PAN-UAT_003 |  | FAIL
A-PAN-UAT_004 |  | FAIL
A-PAN-UAT_005 |  | FAIL
A-PAN-UAT_006 |  | FAIL
Test sign-off: | Erin Fredericks
Development and Compliance Support Coordinator
erin.fredericks@portstephens.nsw.gov.au
02 4988 0239

## A-PAN-UAT_001
Tested by: | Erin Fredericks
Test date: | 2025-07-08
Test scenario: | A council officer uploads LEC documentation to an offline DA
Test step |  | Expected result | Pass/ Fail If the test step fails, please include a screenshot in this file. | Comments
1. Log into the NSW Planning Portal test environment by: a) Open UAT environment: https://apps-uat.planningportal.nsw.gov.au/prweb/PRAuth/PlanningSSO b) Enter username: council13.uat2025@yopmail.com c) Enter password: rules@123 |  | 1. The user can log into the NSW Planning Portal using the information provided 2. The user sees the NSW Planning Portal dashboard (council view) | Pass
2. Select 'Publish on portal' from the 'Create a new application by selecting the relevant digital service from the options below' drop down menu and select 'Create new'. |  | 1. The screen will be open to choose submission type from the drop down menu | Pass
3. Select Land and Environment Court (LEC) documentation from the drop down menu and click 'next' to proceed to the submission details screen. (a) Click 'Save and continue' |  | 1. User can Land and Environment Court (LEC) documentation from the list of drop-down options 2. User can see the submission details screen to populate all mandatory fields | Pass
4. In the development application details stage, and complete all mandatory fields. (a) Click 'Save and continue' |  | 1. User can see the submission details screen to populate all mandatory fields 2. User is moved to the next screen | Pass
5. Complete the 'upload documents details' screen. (a) Click 'Save and continue' (b) Write down the reference number in column E Notes: * You can edit any pre-populated information based on your profile |  | 1. There is a system generated reference number starting with 'PEH-' in the red banner at top of screen 2. Status in red banner is 'In progress' 3. Actions menu options are Refresh and 'Cancel application' 4. 'Cancel' button is displayed at the bottom of the screen 5. Council details pre-populated based on the user profile information can be amended 6. User able to click 'Save and continue' when all mandatory fields have been input 7. Unable to progress application if mandatory fields not completed |  | A-PAN-246 - FAIL - would not let me continue
5. Complete the 'Submission details' review screen. Please ensure you select the following: * Submission type = LEC documents * Mandatory fields are populated Click 'Save and continue'. |  | 1. User can only select one submission type 2. User can see the status of the submission change to resolved 3. User confirms email notification receipt 4. Application status is changed to 'Notified'
Related resources | How to upload Land and Environment Court documents
Navigating the NSW Planning Portal dashboard

## A-PAN-UAT_002
Tested by: | Erin Fredericks
Test date: | 2025-07-08
Test scenario: | A council officer uploads an annual statement for contribution plans
Test step |  | Expected result | Pass/ Fail If the test step fails, please include a screenshot in this file. | Comments
1. If you have logged out between test scenarios, log into the NSW Planning Portal test environment by: a) Open UAT environment: https://apps-uat.planningportal.nsw.gov.au/prweb/PRAuth/PlanningSSO b) Enter username: council13.uat2025@yopmail.com c) Enter password: rules@123 |  | 1. The user can log into the NSW Planning Portal using the information provided 2. The user sees the NSW Planning Portal dashboard (council view) | Pass
2. Select 'Publish on portal' from the 'Create a new application by selecting the relevant digital service from the options below' drop down menu and select 'Create new'. (a) Select annual statements from dropdown (b) Enter year of document dd/mm/yy |  | 1. The screen will be open to choose submission type from the drop down menu 2. User will be prompted to enter year of document | Pass
3. In the 'Application Submission' stage, upload documents and complete all mandatory fields. Click 'Save and continue'. |  | 1. Entered details are saved in Applicant Details screen 2. Documents are successfully uploaded 3. User is moved to the next screen (Application Details) | Pass
4. Complete the 'Development application details' screen. (a) Click 'Save and continue' (b) Write down the reference number in column E Notes: * You can edit any pre-populated information based on your profile |  | 1. There is a system generated reference number starting with 'PEH-' in the red banner at top of screen 2. Status in red banner is 'In progress' 3. Actions menu options are Refresh and 'Cancel application' 4. 'Cancel' button is displayed at the bottom of the screen 5. Council details pre-populated based on the user profile information can be amended 6. User able to click 'save and continue' when all mandatory fields have been input 7. Unable to progress application if mandatory fields not completed | Pass | PEH-1013
5. Complete the 'Submission details' review screen. Please ensure you select the following: * Submission type = Annual statement for contribution plans * Mandatory fields are populated Click 'Save and continue'. |  | 1. User can only select one submission type 2. User can see the status of the submission change to resolved 3. User confirms email notification receipt 4. Application status is changed to 'Notified' |  | It wouldn't let me any of these details at all. It just went through and was published. Red banner changed to Notified
Related resources
Navigating the NSW Planning Portal dashboard

## A-PAN-UAT_003
Tested by: | Erin Fredericks
Test date: | 2025-07-08
Test scenario: | A council officer uploads an annual report for contribution plans
Test step |  | Expected result | Pass/ Fail If the test step fails, please include a screenshot in this file. | Comments
1. If you have logged out between test scenarios, log into the NSW Planning Portal test environment by: a) Open UAT environment: https://apps-uat.planningportal.nsw.gov.au/prweb/PRAuth/PlanningSSO b) Enter username: council13.uat2025@yopmail.com c) Enter password: rules@123 |  | 1. The user can log into the NSW Planning Portal using the information provided 2. The user sees the NSW Planning Portal dashboard (council view) | Pass
2. Select 'Publish on portal' from the 'Create a new application by selecting the relevant digital service from the options below' drop down menu and select 'Create new'. (a) Select annual reports for contribution plans from dropdown (b) Enter year of document dd/mm/yy |  | 1. The screen will be open to choose submission type from the drop down menu 2. User will be prompted to enter year of document | Pass
3. In the 'Application Submission' stage, upload documents and complete all mandatory fields. Click 'Save and continue'. |  | 1. Entered details are saved in Applicant Details screen 2. Documents are successfully uploaded 3. User is moved to the next screen (Application Details) | Pass | No applicant details screen - jut upload documents and required documents
4. Complete the 'Development application details' screen. (a) Click 'Save and continue' (b) Write down the reference number in column E Notes: * You can edit any pre-populated information based on your profile |  | 1. There is a system generated reference number starting with 'PEH-' in the red banner at top of screen 2. Status in red banner is 'In progress' 3. Actions menu options are Refresh and 'Cancel application' 4. 'Cancel' button is displayed at the bottom of the screen 5. Council details pre-populated based on the user profile information can be amended 6. User able to click 'save and continue' when all mandatory fields have been input 7. Unable to progress application if mandatory fields not completed |  | No council details
5. Complete the 'Submission details' review screen. Please ensure you select the following: * Submission type = Annual report for contribution plans * Mandatory fields are populated Click 'Save and continue'. |  | 1. User can only select one submission type 2. User can see the status of the submission change to resolved 3. User confirms email notification receipt 4. Application status is changed to 'Notified' | Pass
Related resources
Navigating the NSW Planning Portal dashboard

## A-PAN-UAT_004
Tested by: | Erin Fredericks
Test date: | 2025-07-08
Test scenario: | A council officer uploads contribution plans and current contribution rates
Test step |  | Expected result | Pass/ Fail If the test step fails, please include a screenshot in this file. | Comments
1. If you have logged out between test scenarios, log into the NSW Planning Portal test environment by: a) Open UAT environment: https://apps-uat.planningportal.nsw.gov.au/prweb/PRAuth/PlanningSSO b) Enter username: council13.uat2025@yopmail.com c) Enter password: rules@123 |  | 1. The user can log into the NSW Planning Portal using the information provided 2. The user sees the NSW Planning Portal dashboard (council view) | Pass
2. Select 'Publish on portal' from the 'Create a new application by selecting the relevant digital service from the options below' drop down menu and select 'Create new'. (a) Select Contribution plans and rates from dropdown (b) Enter year of document dd/mm/yy |  | 1. The screen will be open to choose submission type from the drop down menu 2. User will be prompted to enter year of document | Pass | PEH-1016
3. In the 'Application Submission' stage, upload documents and complete all mandatory fields. Click 'Save and continue'. |  | 1. Entered details are saved in Applicant Details screen 2. Documents are successfully uploaded 3. User is moved to the next screen (Application Details) |  | item 1 and 2 pass, Item #3, next screen is the declaration
4. Complete the 'Development application details' screen. (a) Click 'Save and continue' (b) Write down the reference number in column E Notes: * You can edit any pre-populated information based on your profile |  | 1. There is a system generated reference number starting with 'PEH-' in the red banner at top of screen 2. Status in red banner is 'In progress' 3. Actions menu options are Refresh and 'Cancel application' 4. 'Cancel' button is displayed at the bottom of the screen 5. Council details pre-populated based on the user profile information can be amended 6. User able to click 'save and continue' when all mandatory fields have been input 7. Unable to progress application if mandatory fields not completed
5. Complete the 'Submission details' review screen. Please ensure you select the following: * Submission type = Contribution plans and current contribution rates * Mandatory fields are populated Click 'Save and continue'. |  | 1. User can only select one submission type 2. User can see the status of the submission change to resolved 3. User confirms email notification receipt 4. Application status is changed to 'Notified'
Related resources
Navigating the NSW Planning Portal dashboard

## A-PAN-UAT_005
Tested by: | Erin Fredericks
Test date: | 2025-07-08
Test scenario: | A council officer uploads annual statement/financial report for planning agreement
Test step |  | Expected result | Pass/ Fail If the test step fails, please include a screenshot in this file. | Comments
1. If you have logged out between test scenarios, log into the NSW Planning Portal test environment by: a) Open UAT environment: https://apps-uat.planningportal.nsw.gov.au/prweb/PRAuth/PlanningSSO b) Enter username: council13.uat2025@yopmail.com c) Enter password: rules@123 |  | 1. The user can log into the NSW Planning Portal using the information provided 2. The user sees the NSW Planning Portal dashboard (council view) | Pass
2. Select 'Publish on portal' from the 'Create a new application by selecting the relevant digital service from the options below' drop down menu and select 'Create new'. (a) Select annual statement/financial report for planning agreement from dropdown (b) Enter year of document dd/mm/yy |  | 1. The screen will be open to choose submission type from the drop down menu 2. User will be prompted to enter year of document | Pass
3. In the 'Application Submission' stage, upload documents and complete all mandatory fields. Click 'Save and continue'. |  | 1. Entered details are saved in Applicant Details screen 2. Documents are successfully uploaded 3. User is moved to the next screen (Application Details) |  | PEH-1017 - same as before - next screen is declaration
4. Complete the 'Development application details' screen. (a) Click 'Save and continue' (b) Write down the reference number in column E Notes: * You can edit any pre-populated information based on your profile |  | 1. There is a system generated reference number starting with 'PEH-' in the red banner at top of screen 2. Status in red banner is 'In progress' 3. Actions menu options are Refresh and 'Cancel application' 4. 'Cancel' button is displayed at the bottom of the screen 5. Council details pre-populated based on the user profile information can be amended 6. User able to click 'save and continue' when all mandatory fields have been input 7. Unable to progress application if mandatory fields not completed
5. Complete the 'Submission details' review screen. Please ensure you select the following: * Submission type = Annual statement/financial report for planning agreement * Mandatory fields are populated Click 'Save and continue'. |  | 1. User can only select one submission type 2. User can see the status of the submission change to resolved 3. User confirms email notification receipt 4. Application status is changed to 'Notified'
Related resources
Navigating the NSW Planning Portal dashboard

## A-PAN-UAT_006
Tested by: | Erin Fredericks
Test date: | 2025-07-08
Test scenario: | A council officer uploads Planning agreement and explanatory notes
Test step |  | Expected result | Pass/ Fail If the test step fails, please include a screenshot in this file. | Comments
1. If you have logged out between test scenarios, log into the NSW Planning Portal test environment by: a) Open UAT environment: https://apps-uat.planningportal.nsw.gov.au/prweb/PRAuth/PlanningSSO b) Enter username: council13.uat2025@yopmail.com c) Enter password: rules@123 |  | 1. The user can log into the NSW Planning Portal using the information provided 2. The user sees the NSW Planning Portal dashboard (council view) | Pass
2. Select 'Publish on portal' from the 'Create a new application by selecting the relevant digital service from the options below' drop down menu and select 'Create new'. (a) Select Planning agreement and explanatory notes from dropdown (b) Enter name of document |  | 1. The screen will be open to choose submission type from the drop down menu 2. User will be prompted to enter name of document | Pass | PEH-1018
3. In the 'Application Submission' stage, upload documents and complete all mandatory fields. Click 'Save and continue'. |  | 1. Entered details are saved in Applicant Details screen 2. Documents are successfully uploaded 3. User is moved to the next screen (Application Details) |  | same as before - next screen is declaration
4. Complete the 'Development application details' screen. (a) Click 'Save and continue' (b) Write down the reference number in column E Notes: * You can edit any pre-populated information based on your profile |  | 1. There is a system generated reference number starting with 'PEH-' in the red banner at top of screen 2. Status in red banner is 'In progress' 3. Actions menu options are Refresh and 'Cancel application' 4. 'Cancel' button is displayed at the bottom of the screen 5. Council details pre-populated based on the user profile information can be amended 6. User able to click 'save and continue' when all mandatory fields have been input 7. Unable to progress application if mandatory fields not completed | NA | PEH-1018
5. Complete the 'Submission details' review screen. Please ensure you select the following: * Submission type = Planning agreement and explanatory notes * Mandatory fields are populated Click 'Save and continue'. |  | 1. User can only select one submission type 2. User can see the status of the submission change to resolved 3. User confirms email notification receipt 4. Application status is changed to 'Notified'
Related resources
Navigating the NSW Planning Portal dashboard